## AGREEMENT

| The Client is |  | Of |
| --- | --- | --- |

| The Contractor is |  | Of |
| --- | --- | --- |

## OFFER

| The Contractor has examined the documents listed in the Appendix which forms part of this Agreement and offers to execute the Works in conformity with the Contract for the sum of: |  |  |
| --- | --- | --- |
|  |  | (in words) |
|  |  | (in figures) |
| Or other such sum as may be ascertained under the Contract. |  |  |

| This offer, of which the Contractor has submitted two originals, may be accepted by the Client by signing and returning one original of this document to the Contractor before: |  |
| --- | --- |
|  | (date) |

The Contractor understands that the Client is not bound to accept the lowest or any offer received for the Works.

| Signature: |  | Date: |  |
| --- | --- | --- | --- |
| Name: |  | Authorised to sign on behalf of (organization name): |  |
| Capacity: |  |  |  |

## ACCEPTANCE

The Client has by signing below, accepted the Contractor’s offer and agrees that in consideration for the execution of Works by the Contractor, the Client shall pay the Contractor in accordance with the Contract. This Agreement comes into effect on the date when the Contractor receives one original of this document signed by the Client.

| Signature: |  | Date: |  |
| --- | --- | --- | --- |
| Name: |  | Authorised to sign on behalf of (organization name): |  |
| Capacity: |  |  |  |

## APPENDIX

This Appendix forms a part of the Contract.

(Note: with the exception of the items for which the Owner’s requirements have been inserted, the Contractor shall complete the following information before submitting his Letter of Tender).

| #### Items | #### Sub-Clause | #### Data |
| --- | --- | --- |

| Documents forming the Contract listed in the order of priority | 1.1.1 |  |
| --- | --- | --- |

| ### Document |  | ### Document Identification |
| --- | --- | --- |
| - The Contract Agreement |  |  |
| - General Conditions |  |  |
| - Preliminaries and Special Conditions of the Contract |  |  |
| - Scope of Works defined |  |  |
| - Bill of Quantities |  |  |
| - The Specifications |  |  |
| - The Drawings |  |  |
| - Reports on Geological |  |  |

| Time for Completion | 1.1.11 | Not exceeding ………… calendar days as from the Commencement Date |  |
| --- | --- | --- | --- |
| Law of the Contract | 1.4 |  |  |
| Language |  |  |  |
| Provision of Site | 2.1 | On signing date of the Contract Agreement |  |
| Authorised Person | 3.1 | General Director of ……………. |  |
| Name and Address of Owner’s Representative (if known) | 3.2 | …………………………. Company |  |

| Performance Security (if any): |  |  |  |
| --- | --- | --- | --- |
| Amount | 4.4 | 10% (ten per cent) of Contract Price |  |
| Form | 4.4 | Bank Guarantee | (Details) |

| Requirements for Contractor’s designs (if any) | 5.1 | Shop drawings |  |
| --- | --- | --- | --- |

| Programme: |  |  |
| --- | --- | --- |
| Time for Submission | 7.2 | Within 7 (seven) days as from the signing date of the Contract Agreement |
| Form of Programme | 7.2 | Gantt Chart |

| Amount payable due to failure of completion | 7.4 | USD…… (…… Dollars) or another amount equivalent to VND……. (……) per day and a maximum of 12% (Twelve per cent) of the Contract Price |  |
| --- | --- | --- | --- |

| Period for notifying defects | 9.1 & 11.5 | As from the date of receipt of the Tender to the expiry of 12 (twelve) calendar months calculated from the date of issuance of the taking-over certificate for the whole of the Project, or when any notified defects have already been remedied or any outstanding works have already been completed, whichever is the later ………….. |
| --- | --- | --- |

| Variation procedure: |  |  |
| --- | --- | --- |
| Daywork rates | 10.2 | Not applicable |

| Contract Value Payments Schedules | 11 |  |
| --- | --- | --- |
| Percentage of value of Materials and Plant | 11.2 | Not Applicable |

| Percentage of retention for guarantee purposes | 11.4 & 11.5 | 5% (five per cent) of Contract Price |  |
| --- | --- | --- | --- |
| Currency of payment | 11.7 | Vietnamese Dong |  |
| Rate of interest | 11.8 | Not Applicable |  |

| Contractor to provide Insurances | 14.1 |  |  |
| --- | --- | --- | --- |

| #### Type of Cover* | #### Amount of Cover* | #### Exclusions |
| --- | --- | --- |
| The Works, Materials, Plant and fees | The sum stated in the contract | Refer to exclusion clauses |
| Contractor’s Equipment | Full replacement cost | Nil |
| Third Party injury to persons and damage to property | Refer to Client Insurance Policy | Refer to exclusion clauses |
| Workers’ Compensation | In accordance with Vietnamese Law | Nil |

| Dispute Settlement |  |
| --- | --- |

| Litigation Rules | 16 |  |  |
| --- | --- | --- | --- |
| Authority having Jurisdiction | 16 |  |  |
| Place of Hearing | 16 |  |  |

GENERAL CONDITIONS

CONTENT

1. GENERAL PROVISIONS

1.1 Definitions 
              The Contract

Persons

Dates, Times and Periods

Money and Payments.

Other Definitions
1.2 Interpretation 
1.3 Priority of Documents 
1.4 Law 
1.5 Communications 
1.6 Statutory Obligations

2. THE CLIENT

2.1 Provision of Site
2.2 Permits and Licenses
2.3 Client’s Instructions 
2.4 Approvals

3. CLIENT’S  REPRESENTATIVES

3.1 Authorised Person 
3.2 Client’s Representative

4. THE CONTRACTOR

4.1 General Obligations 
4.2 Contractor’s Representative 
4.3 Sub-contracting 
4.4 Performance Guarantee

5. DESIGN BY CONTRACTOR

5.1 Contractor’s Design 
5.2 Responsibility for Design

6. CLIENT’S  RISKS

6.1 Client’s Risks

7. TIME FOR COMPLETION

7.1 Execution of the Works 
7.2 Programme 
7.3 Extension of Time 
7.4 Late Completion

8. TAKING-OVER

8.1 Completion 
8.2 Taking-Over Notice

9. REMEDYING DEFECTS

9.1 Remedying Defects 
9.2 Uncovering and Testing

10. VARIATIONS AND CLAIMS

10.1 Right to Vary 
10.2 Valuation of Variations 
10.3 Early warning  
10.4 Variation and Claim Procedure

11. CONTRACT PRICE AND PAYMENT

11.1 Valuation of the Works 
11.2 Payment Terms
11.3 Interim Payment 
11.4 Payment of First Half of Retention 
11.5 Payment of Second Half of Retention 
11.6 Final Payment 
11.7 Currency

11.8 Delayed payment

12. DEFAULT

12.1 Default by Contractor 
12.2 Default by Client 
12.3 Insolvency 
12.4 Payment upon Termination

13. RISK AND RESPONSIBILITY

13.1 Contractor’s Care of the Works
13.2 Force Majeure

14. INSURANCE

14.1 Insurance of Works
14.2 Insurance of Contractor’s Equipment

14.3 Motor Vehicle Third Party Insurance

14.4 Scope of Cover

14.5 Responsibility for Amounts not Recovered.

14.6 Damage to Persons and Property

14.7 Exceptions

14.8 Indemnity by Client

14.9 Third Party Insurance

14.10 Minimum Amount of Insurance

14.11 Cross Liabilities

14.12 Accident or Injury to Workmen

14.13 Insurance Against Accident to Workmen

14.14 Evidence and terms of Insurances

14.15 Adequacy of Insurances

14.16 Remedy on Contractor’s Failure to Insure

14.17 Compliance Policy Conditions

15  RESOLUTION OF DISPUTES

15.1 Adjudication
15.2 Notice of Dissatisfaction
15.3 Arbitration

GENERAL CONDITIONS

I 	GENERAL CONDITIONS

1.1 	Definitions

In the Contract as defined below, the words and expression defined shall have the following meanings assigned to them, except where the context requires otherwise:

The Contract

    - “Contract”	 means the Agreement and the other documents listed in the Appendix.

    - “Specification” means the document as listed in the Appendix, including the Client’s requirements in respect of design to be carried out by the Contractor, if any, and any Variation to such document.

    - “ Drawings” means the Client’s drawings of the Works as listed in the Appendix, and any Variation to such drawings

Persons

    - “The Client” means the person named in the Agreement and the legal successors in title to this person, but not (except with the consent of the Contractor) any assignee.

    - “Contractor” means the person named in the Agreement and the successors in title to this person, but not (except with the consent of the Client) any assignee.

    - “ Party” means either the Client or the Contractor

Dates, Times, and Periods

    - “Commencement Date” means the date 14 days after the date the Agreement comes into effect or any other date agreed between the Parties.

    - “Day” means a calendar day

    - “Time for Completion” means the time for completing the Works as stated in the Appendix (or as extended under Sub- Clause 7.3), calculated from the Commencement date.

Money and Payments

    - “Cost” means all expenditure properly incurred (or to be incurred) by the Contractor, whether on or off the site, including overheads and similar charges, but does not include profit.

Other definitions

    - “Contractor’s equipment” means all apparatus, machinery, vehicles, facilities and other things required for the execution of the Works but does not include Materials or Plant.

    - “ Country” means the country in which the Site is located

    - “ Client’s Liabilities” means those matters listed in Sub- Clause 6.1

    - “Force Majeure” means an exceptional event or circumstance: which is beyond a Party’s control; which such Party could not reasonably have provided against before entering into the Contract, which, having arisen, such Party could not reasonably have avoided or overcome; and, which is not substantially attributable to the other Party.

    - “Materials” means things of all kinds (other than plant) intended to form or forming part of the permanent work.

    - “Plant” means the machinery and apparatus intended to form or forming part of the permanent work.

    - “ Site” means the places provided by the Client where the works are to be executed, and any other places specified in the Contract as forming part of the Site.

    - “Variation” means a change  to the Specification and/or  drawings ( if any) which is instructed by the Client under Sub- Clause 10.1

    - “Works” means all the work and design ( if any) to be performed by the Contractor including temporary work and any variation

  - Interpretation

Words importing persons or parties shall include firms and organisations. Words importing singular or one gender shall include plural or the other gender where the context requires.

  - Priority of Documents

The documents forming the Contract are to be taken as mutually explanatory of one another. If an ambiguity or discrepancy is found in the documents, the Client shall issue any necessary instructions to the Contractor, and the priority of the documents shall be in accordance with the order as listed in the Appendix.

  - Law

The law of the Contract is stated in the Appendix.

  - Communications

Wherever provision is made for the giving or issue of any notice, instruction, or other communication by any person, unless otherwise specified such communication shall be written in the language stated in the Appendix and shall not be unreasonably withheld or delayed.

  - Statutory Obligations

The Contractor shall comply with the laws of the countries where activities are performed. The Contractor shall give all notices and pay all fees and other charges in respect of the Works.

2	THE CLIENT

2.1	Provision of site

The Client shall provide the Site and right of access thereto at the times stated in the Appendix

  - Permits and Licences

The Client shall, if requested by the Contractor, assist him in applying for permits, licences or approvals which are required for the works

  - Client’s Instructions

The Contractor shall comply with all instructions given by the Client in respect of the Works including the suspension of all or part of the works

  - Approvals

No approval or consent or absence of comment by the Client or the Client’s representative shall affect the Contractor’s obligations.

3	CLIENT’S  REPRESENTATIVES

  - Authorised person

One of the Client’s personnel shall have authority to act for him. This authorised person shall be as stated in the Appendix, or as otherwise notified by the Client to the Contractor.

  - Client’s  Representative

The Client may also appoint a firm or individual to carry out certain duties. The appointee may be named in the Appendix, or notified by the Client to the Contractor from time to time. The Client shall notify the Contractor of the delegated duties and authority of this Client’s representative.

4	THE CONTRACTOR

  - General Obligations

The Contractor shall carry out the Works properly and in accordance with the Contract. The Contractor shall provide all supervision, labour, Materials, Plant and Contractor’s Equipment which may be required. All materials and plant on Site shall be deemed to be the property of the Client.

  - Contractor’s Representative

The Contractor shall submit to the Client for consent the name and particulars of the person authorised to receive instructions on behalf of the Contractor.

  - Subcontracting

The Contractor shall not subcontract the whole of the Works. The Contractor shall not subcontract any part of the Works without the consent of the Client.

4.4	Performance Guarantee

If stated in the Appendix, the Contractor shall deliver to the Client prior to signing of the Contract  a performance guarantee in a form and from a third party approved by the Client.

5	DESIGN BY CONTRACTOR

  - Contractor’s Design

The Contractor shall carry out design to the extent specified, as referred to in the Appendix. The Contractor shall promptly submit to the Client all designs prepared by him. Within 14 days of receipt the Client shall notify any comments or, if the design submitted is not in accordance with the Contract, shall reject it stating the reasons. The Contractor shall not construct any element of the permanent work designed by him within 14days after the design has been submitted to the Client or where the Design for that element has been rejected. Design that has been rejected shall be promptly amended and resubmitted. The Contractor shall resubmit all designs commented on taking these comments into account as necessary.

  - Responsibility for Design

The Contractor shall remain responsible for his tendered design and the design under this Clause, both of which shall be fit for the intended purposes defined in the Contract and he shall also remain responsible for any infringement of any patent or copyright in respect of the same. The Client shall be responsible for the specification and Drawings.

6	CLIENT’S  RISKS

  - Client’s  Risks

In this Contract, Client  risks :

Insofar as they directly affect the execution of the Works and have not and reasonably cannot be insured against:

- War and hostilities ( whether war be declared or not), invasion, acts of foreign enemies, within the Country

- Rebellion, terrorism, revolution, insurrection, military or usurped power, or civil war, within the country

- Riot, commotion or disorder by persons other than the Contractor’s personnel and other employees, affecting the Site and/or the Works.

- Ionising radiations, or contamination by radio- activity from any nuclear fuel, or from any nuclear waste from the combustion of nuclear fuel, radio- active toxic explosive, or other hazardous properties of any explosive nuclear assembly or nuclear component of such an assembly, except to the extent to which the Contractor may be responsible for the use of any radio – active material.

- Pressure waves caused by aircraft or other aerial devices travelling at sonic or supersonic speeds.

- Use or occupation by the Client of any part of the Works, except as may be specified in the contract

- Design of any part of the Works by the Client’s personnel or by others for whom the Client is responsible, and

- Losses arising out of the Client’s right to have the permanent work executed on, over, under, in or through any land, and to occupy this land for the permanent work ,and

7	TIME FOR COMPLETION

  - Execution of the Works

The Contractor shall commence the works on the Commencement date and shall proceed expeditiously and without delay and shall complete the Works within the Time for Completion.

  - Programme

Within the time stated in the Appendix, the Contractor shall submit to the Client a programme for the Works in the form stated in the Appendix.

  - Extension of Time

Subject to Sub – Clause 10.3, The Contractor shall be entitled to an extension to the time for completion if he is or will be delayed by any of the following events:

- the amount or nature of extra or additional work (for avoidance of doubt excluding any work necessary to overcome a defect or deficiency in the Works);

- a Force Majeure delay under Clause 13.2 (Force Majeure);

- any delay due to Client’s Risk under Clause 6.1 (Client’s Risks);

- any instructions of the Client or Client’s Representative to suspend the Works, where such suspension is due to matters beyond the control of the Contractor ;

- any other act or omission of the Client or employee,agent or consultant of the Client, not covered above;or

- a breach of the Contract by the Client;

On receipt of an application from the Contractor, the Client shall consider all supporting details provided by the Contractor and shall extend the Time for Completion as appropriate. In making such determination, the Client shall take into consideration whether the Contractor acted reasonably to mitigate the delaying effect of such events .

  - Late Completion

If the Contractor fails to complete the Works within the Time for Completion, the Contractor’s only liability to the Client for such failure shall be to pay the amount stated in the Appendix for each day for which he fails to complete the Works.

8	TAKING –OVER

  - Completion

The Contractor may notify the Client when he considers that the Works are complete.

  - Taking – over Notice

The Client shall notify the Contractor when he considers that the Contractor has completed the Works stating the date accordingly. Alternatively, the Client may notify the Contractor that the Works, although not fully complete, are ready for taking over, stating the date accordingly.

The Client  shall take over the Works upon the issue of this notice. The Contractor shall promptly complete any outstanding work and, subject to Clause 9, clear the Site.

9	REMEDYING DEFECTS

9. 1	Remedying Defects

The Client may at any time prior to the expiry of the period stated in the Appendix, notify the Contractor of any defects or outstanding work. The Contractor shall remedy at no cost to the Client any defects due to the Contractor‘s design, materials, Plant or workmanship not being in accordance with the Contract.

The cost of remedying defects attributable to any other cause shall be valued as a Variation. Failure to remedy any defects or complete outstanding work within a reasonable time of the Client’s notice shall entitle the Client to carry out all necessary work at the Contractor‘s cost.

9.2	Uncovering and Testing

The Client  may give instruction as to the uncovering and/ or testing of any work. Unless as a result of any uncovering and/ or testing it is established that the Contractor’s design, Materials, Plant  or workmanship are not in accordance with the Contract, the Contractor shall be paid for such uncovering and/ or testing as a Variation  in accordance with Sub – Clause 10.2.

10	VARIATIONS AND CLAIMS

  - Right to Vary

The Client  may instruct Variations.

  - Valuations of Variations

Variations shall be valued as follows:

- At a lump sum price agreed between  the Parties, or

- Where appropriate, at rates in the Contract, or

- In the absence of appropriate rates, the rates in the Contract shall be used as the basis for Variations, or failing  which

- At appropriate new rates, as may be agreed or which the Client considers appropriate, or

- If the Client so instructs, at day work rates set out in the Appendix for which the Contractor shall keep records of hours of labour and Contractor‘s Equipment, and of materials used.

  - Early warning

A  Party shall notify the other as soon as he is aware of any circumstance which may delay or disrupt the Works, or which may give rise to a claim for additional payment. The Contractor shall take all reasonable steps to minimise these effects.

The Contractor‘s entitlement to extension to the Time for Completion or additional payment shall be limited to the time and payment which would have been due if he had given prompt notice and had taken all reasonable steps.

  - Variation and Claim Procedure

The Contractor shall submit to the Client an itemised make –up of the value of Variations and claims within 28 days of the instruction or of the event giving rise to the claim. The Client shall check and if possible agree the value. In the absence of agreement, The Client shall determine the value.

11	CONTRACT PRICE AND PAYMENT

  - Valuation of the works

The Works shall be valued as provided for in the Appendix, subject to Clause 10

  - Payment Terms

The Contractor shall be entitled to be paid at  intervals stated in the Appendix:

- The percentage value of the Works executed in accordance with the payment schedule.

Subject to any additions or deductions which may be due.

The Contractor shall submit to the Client in accordance with the percentages stated in the payment schedule detailed in the Appendix a statement showing the amounts to which he considers himself entitled.

The said statement shall be approved or amended by the Client’s Representative in such a way that, in his opinion, it reflects the amounts due to the Contractor in accordance with the Contract, after deduction of any sums which may have become due and payable by the Contractor to the Client. In cases where there is a difference of opinion as to the value of any item, the Client Representative’s  view shall prevail. Within fourteen (14)  days of receipt of the  statement  referred to in above  the Client’s representative  shall determine the amounts due to the Contractor and shall issue to the Client and the Contractor a certificate herein called the “Interim Payment Certificate”, certifying the amounts due to the Contractor.

  - Interim payments

Within 28 days of delivery of each statement, The Client shall pay to the Contractor the amount shown in the Client’s  “Interim Payment Certificate” less retention at the rate  stated in the Appendix, and less any amount for which the Client has specified his reasons for disagreement. The Client shall not be bound by any sum previously considered by him to be due to the Contractor,

The Client may withhold interim payments until he receives the performance guarantee under Sub- clause 4.4 (if any)

  - Payment of first half of retention

One half of the retention shall be paid by the Client to the Contractor within 28 days after completion of  Pile Cap construction by the  Clients appointed Contractor.

  - Payment of second half of retention

The remainder of the retention shall be paid by the Client to the Contractor within 28 days after the issuance of the Taking Over Certificate for the Main Contract Works , or the remedying of notified defects or the completion of outstanding  work , all  as referred to in Sub- clause 9.1, whichever is the later.

  - Final payment

Within 42 days of the latest of the events listed in Sub – clause 11.5 above, the Contractor shall submit a final account to the Client together with any documentation reasonably required to enable the Client to ascertain the final contract value.

Within 28 days after the submission of this final account, the Client shall pay to the Contractor any amount due. If the Client disagrees with any part of the Contractor‘s final account, he shall specify his reasons for disagreement when making payment.

  - Currency

Payment shall be in the currency stated in the Appendix.

  - Delayed payment

The Contractor shall not be entitled to interest  for each day the Client fails to pay beyond the prescribed payment period.

12	DEFAULT

  - Default by Contractor

If the Contractor abandons  the Works, refuses or fails to comply with a valid instruction of the Client or fails to proceed expeditiously and without delay, or is, despite a written complaint, in breach of the Contract, the Client may give notice referring to this sub – clause and stating the default.

If the Contractor has not taken all practicable steps to remedy the default within 7 days after the Contractor ‘s receipt of the Client’s notice, the Client may by a second notice given within a further 7 days, terminate the contract. The Contractor shall then demobilise from the Site leaving behind materials and plant and any Contractor‘s equipment which the Client instructs in the second notice is to be used until the completion of the Works

  - Default by Client

If the Client fails to pay in accordance with the Contract, or is, despite a written complaint, in breach of the Contract, the Contractor may give notice referring to this Sub – Clause and stating the default. If the default is not remedied within 56 days after the Client’s receipt of this notice, the Contractor may suspend the execution of all or parts of the Works.

If the default is not remedied within 28 days after the Client’s receipt of the Contractors notice, the Contractor may by a second notice given within a further 21 days, terminate the Contract. The Contractor shall then demobilise from the Site.

  - Insolvency

If a Party is declared insolvent under any applicable law, the Other Party may by notice terminate the Contract immediately. The Contractor shall then demobilise from the Site leaving behind, in the case of the Contractor‘s insolvency, any Contractor’s Equipment which the Client instructs in the notice is to be used until the completion of the Works.

  - Payment upon Termination

After termination, the Contractor shall be entitled to payment of the unpaid balance of the value of the Works executed and of the Materials and Plant reasonably delivered to the Site, adjusted by the following:

- Any sums  to which the Contractor is entitled under Sub – Clause 10.4

- Any sums to which the Client is entitled

- If the Client has terminated under sub – clause 12.1 or 12.3, the Client shall be entitled to a sum equivalent to 20% of the value of those parts of the Works not executed at the date of the termination.

- If the Contractor has terminated under  sub- clause 12.2 or 12.3, the Contractor shall  be entitled to the Cost of his suspension and demobilisation together  with a sum equivalent to 10% of the value of those parts of the Works not executed at the date of termination

The net balance due shall be paid or repaid within 28 days of the notice of termination.

13	RISK AND RESPONSIBILITIES

  - Contractor’s care of the works

The Contractor shall take full responsibility for the care of the Works from the Commencement date until the date of the Client’s notice under Sub- clause 8.2. Responsibility shall then pass to the Client. If any loss or damage happens to the Works during the above period, the Contractor shall rectify such loss or damage so that the Works conform to the contract.

Unless the loss or damage happens as a result of an Client’s Liability, the Contractor shall indemnify the Client, the Client’s contractors, agents, and employees against all loss or damage happen in to the Works and against all claims or expense arising out of the Works caused by a breach of the Contract, by negligence or by other default of the Contractor, his agents or employees.

  - Force Majeure

If a Party is or will be prevented from performing any of its obligations by Force Majeure, the Party affected shall notify the other Party immediately. If necessary, the Contractor shall suspend the execution of the Works and, to the extent agreed with the Client, demobilise the Contractor ‘Equipment.

Such events ,occurrences fall within the following categories:

- Natural calamities such as fires , floods, earthquakes, cyclones, explosions or lightning;

- Riot, commotion, disorder or labour unrest or strike, unless restricted to the employees of Contractors or Subcontractors employed on the Project; or

- Other events in the nature of Force Majeure wholly and demonstrably beyond the control and without the fault or negligence of both (1) the party claiming Force Majeure, and (2) any Subcontractor, sub-subcontractor, agent, employee or other person for whom the party claiming Force Majeure is responsible.

The party claiming Force Majeure shall take such actions as they may reasonably and lawfully initiate to remove or relieve, in whole or in part, either the Force Majeure occurrence or its direct or indirect effects. A Force Majeure delay as defined herein shall be considered  an excusable delay and shall entitle the party experiencing such delay to a time extension in accordance with clause 7.3, but neither party shall be entitled to additional compensation or any adjustment of the Contract Price as a result thereof.

If the event continues for a period of 84 days, either Party may the give notice of termination which shall take effect 28 days after the giving of the notice.

After termination, The Contractor shall be entitled to payment of the unpaid balance of the value of the Works executed and of the Materials and Plant reasonably delivered to the site, adjusted by the following:

- Any sums  to which the Contractor is entitled under Sub – Clause 10.4.

- Any sums to which the Client is entitled.

The net balance due shall be paid or repaid within 28 days of the notice of termination.

14	INSURANCE

  - Insurance of Works

Without limiting his or the Contractor’s obligations and responsibilities under Clauses 6.1 and 13.1 , the Client will insure:

- The Works, together with materials and plant for incorporation therein, to the full replacement cost; and

- An additional sum to cover any additional costs of and incidental to the rectification of loss and damage including professional fees and the cost of demolishing and removing any part of the Works and of removing debris of whatsoever nature.

14.2    Insurance of Contractor’s Equipment

The Contractor shall, without limiting his obligations and responsibilities   under Clause 13.1 , insure the Contractor’s equipment and other things brought onto the Site by the Contractor, for a sum sufficient to provide for their replacement at the Site.

14.3	Motor Vehicle Third Party Insurance

The Contractor shall effect Motor Vehicle Third Party Insurance for an amount  of not less than the maximum amount available from Insurers licensed to conduct business in Vietnam in respect of all motor vehicles( which expression shall include any item of plant or equipment which is licensed as a motor vehicle or which is licensed by any Vietnamese law) used by the Contractor or any other person , whether or not owned by the Contractor or in connection with the execution of the Works or in fulfilling its obligations under this Contract or any activity directly or indirectly connected with the Works.

14.4	Scope of Cover

The insurance in sub-clause 14.1 shall be in the name of the Client and shall    cover the Client, the Contractor’s and it’s Sub-contractors and suppliers against all risks of physical loss of damage to the Work under or in the course of construction from the start of Work at the Site until the date of issue of the relevant Taking-Over Certificate in respect of the Work or any Section or part thereof as the case may be. Details of the Clients Insurance Program are included in Part 7 of Contract Attachments.

  - Responsibility for Amounts not Recovered

Any amounts not insured or not recovered from the Insurers shall be borne by the Client or the Contractor in accordance with their responsibilities under Clauses 6.1 and 13.1.

14.6	Damage to Persons and Property

The Contractor shall, except if and so far as the Contract provides otherwise , indemnify the Client and the Construction Manager against all losses and claims in respect of:

  - death of or injury to any person; or

  - loss of or damage to any property(other than the Works),

which may arise out of or in consequence of the execution and completion of the Works and the remedying of any defects therein, and against all claims, proceedings, damages, costs, charges and expenses whatsoever in respect  thereof or in relation thereto, subject to the exceptions defined in Sub-clause 14.7.

  - Exceptions

The “exceptions” referred to in Sub-clause 14.6 are:

  - the permanent use or occupation of land by the Works, or any part thereof;

  - the right of the Client to execute the Works, or any part thereof, on, over , under, in or through any land;

  - damage to property which is the unavoidable result of the design of the Works, or in remedying of any defects therein, in accordance with the Contract (other than works designed by the Contractor of those for whom he is responsible); and

  - death of or injury to persons or loss of or damage to property resulting solely from any act or neglect of the Client, his agents or other contractors , not being engaged by the Contractor.

  - Indemnity by Client

The Client shall indemnify the Contractor against all claims, proceedings, damages, costs, charges and expenses in respect of the matters referred to in the exceptions defined in Sub-clause 14.7.

14.9	Third Party Insurance

Without limiting his or the Contractor’s obligations and responsibilities under Clause 13.1, the Client will insure in the name of the Client and covering the Client, the Contractor and its Subcontractors and suppliers, against liabilities for death of or injury to any person (other than as provided in Clause 14.12) or loss of or damage to any property (other than the Works) arising out of the performance of the Contract, as provided in the details of insurance referred to in Sub-clause 14.4.

  - Minimum Amount of Insurance

Such insurance shall be for at least the amount stated in the Appendix to Conditions of Contract, and shall be on an “occurrence” based form.

  - Cross Liabilities

The insurance policy shall include a cross liability clause such that the insurance shall apply to the Construction Manager and to the Client as separate insureds. The Client and the Contractor hereby waive all rights against each other, and against any agents, employees, Subcontractors, each of the other , and against the Construction Manager and any of its agents, employees and subcontractors , for damages to the extent such damages are covered by the proceeds from insurances obtained pursuant to Clause 14.1, except with respect to their rights, if any, to the proceeds of such insurance.

  - Accident or Injury to Workmen

The Client shall not be liable for or in respect of any damages or compensation payable to any workman or other person in the employment of the Contractor or any Subcontractor , other than death or injury resulting from any act or default of the Client, his agents or servants. The Contractor shall indemnify and keep indemnified the Client against all such damages and compensation , other than those for which the Client is liable as aforesaid , and against all claims, proceedings , damages, costs, charges, expenses whatsoever in respect thereof or in relation thereto.

  - Insurance Against Accident to Workmen

The Contractor shall insure against such liability and shall continue such insurance during the whole of the time that any persons are employed by him on the Works. Provided that, in respect of any persons employed by any Subcontractor, the Contractor’s obligations to insure as aforesaid under this Sub- Clause shall be satisfied if the Subcontractor  shall have insured against liability  in respect of such persons in such manner that the Client is indemnified under the Policy, but the Contractor  shall require such Subcontractor  to produce to the Client, when required, such policy of insurance and the receipt  for the payment of the current premium.

  - Evidence and Terms of Insurances

The Contractor shall provide evidence to the Client prior to the commencement of Establishment on Site that the insurances required under the Contract have been effected . The Contractor shall effect all insurances for which he is responsible with insurers and on terms approved by the Client.

  - Adequacy of Insurances

The Contractor shall notify the insurers of changes in the nature, extent of programme for the execution of the Works and ensure the adequacy of the insurances at all times in accordance with the terms of the Contract and shall , when required, produce to the Client  the insurance policies in force and the receipts for payment of the current premiums.

14.16	Remedy on Contractor’s Failure to Insure

If the Contractor fails to effect and keep in force any of the insurances required under the Contract , or fails to provide the policies to the Client within the period required by Sub-Clause 14.14 then in any such case the Client may effect and keep in force any such insurances and pay any premium as may be necessary for that purpose and from tome to time deduct the amount so paid from monies due or to become due to the Contractor, or recover the same as a debt from the Contractor. Any use or non-use of this remedy by the Client shall not relieve  the Contractor of any of his responsibilities under the Contract relating to provision of insurances.

  - Compliance with Policy Conditions

In the event that the Contractor or the Client fails to comply with the   conditions imposed by the insurance policies effected  pursuant to the Contract, each shall indemnify the other against all losses and claims arising from such failure.

15	RESOLUTION OF DISPUTES

  - Adjudication

Unless settled amicably, any dispute or difference which arises between the Contractor and the Client out of or in connection with the Contract, including any valuation or other decision of the Client, shall be referred by either Party to adjudication in accordance with the attached Rules for Adjudication (“the Rules”). The adjudicator shall be any person agreed by the Parties. In the event of disagreement, the adjudicator shall be appointed in accordance with the Rules.

  - Notice of Dissatisfaction

If a Party is dissatisfied with the decision of the adjudicator or if no decision is given within the time set out in the Rules, the Party may give notice of dissatisfaction referring to this Sub- Clause within 28 days of receipt of the decision or the expiry of the time for the decision. If no notice of dissatisfaction is given within the specified time, the decision shall be final and binding on the Parties. If notice of dissatisfaction is given within the specified time, the decision shall be binding on the Parties who shall give effect to it without delay unless and until the decision of the adjudicator is revised by an arbitrator.

  - Arbitration

A dispute which has been the subject of a notice of dissatisfaction shall be finally settled by a single arbitrator under the rules specified in the Appendix. In the absence of agreement, the arbitrator shall be designated by the appointing authority specified in the Appendix. Any hearing shall be held at the place specified in the Appendix and in the language referred to in Sub- Clause 1.5